## Instructions
Instructions:
1 | Save file immediately as devcrew_BOCv1 i.e. superStars_BOCv1
2 | Use the Development Schedule worksheet and populate this sheet with the use case numbers - list the use case names & numbers under the heading Use Case Glossary in Column A Group the Use Case according to the allocated Dev Crew Member
3 | The dates indicate when you commit to have completed the implementation of the use case(s), this will be used for progress check purposes
4 | The data in columns B-E, S-AA MUST NOT be changed - this is the same for all students and all dev crews
5 | Refer to the examples on Funda

## Development Schedule
Backlog Ownership Chart Implementation Planning
Essential Minds
[5 empty] | Exam Period Commit to at least 1 use case |  |  | Recess Commit to at least 2 use cases |  |  |  |  | Sprint Review 2 [Formal]
Crew Member | 4 - 8 May | 11 - 15 May | 18 - 22. May | 25 - 29 May | 1 - 5 Jun | 8 - 12 Jun | 15 - 19 Jun | 22 - 26 Jun | 29 Jun - 3 Jul | 7 - 11 Jul | 13 - 17 Jul | 20 - 24 Jul | 27 - 31 Jul | 4 - 7 Aug | 10 - 14 Aug | 17 - 21 Aug | 24 - 26 Aug | Recess (27 Aug - 2 Sep) | 3 - 5 Sep | 7 - 11 Sep | 14 - 18 Sep | 21 - 25 Sep | 28 Sep - 2 Oct | 5 - 9 Oct | 12 - 16 Oct | Fri, 16 Oct @ 13:00 Project Due
Hlomani Mashimbye | Database Implementation Setup environment, stylesheets, create master pages, logins & dashboards, etc |  |  |  |  | UC01_SI | UCO2_SI |  | UC04_S UC05_S | UC16_A |  |  |  |  | UC03_S | UC17_A |  | Start Integration |  | Integration Checks & Testing |  |  |  | Project Retrospective | Get ready for Submission
Awonke Gana | [6 empty] | UC11_I | UC12_SI |  |  | UC14_I | UC11_SI |  | UC20_I | UC09_I |  | UC19_A
Lethabo Mathole | [9 empty] | UC06_S UC13_I | UC07_S |  | UC08_S | UC15_IA UC18_A |  | UC10_S
Use Case Glossary
UC01_S | Register |  |  |  | Register Account
UC02_SI | Book accomodation |  |  |  | Edit Profile
UC04_S | Make payment |  |  |  | Search Instructor
UC05_S | Generate receipt |  |  |  | View Instructor Profile
UC16_A |  |  |  |  | Review Instructor Application
UC03_S |  |  |  |  | View Lesson Progress
UC17_A
UC11_I |  |  |  |  | Manage Availability
UC12_I |  |  |  |  | Manage Lesson Offering
UC14_I |  |  |  |  | Respond to Booking Requests
UC11_SI |  |  |  |  | Manage Bookings
UC20_I |  |  |  |  | Provide Lesson Feedback
UC09_S |  |  |  |  | View Completed Lessons
UC19_A |  |  |  |  | Monitor Bookings
UC06_S |  |  |  |  | Make Booking Request
UC13_I |  |  |  |  | View Booking Requests
UC07_S |  |  |  |  | View Booking Status
UC08_S |  |  |  |  | Upload Proof of Payment
UC15_IA |  |  |  |  | Verify Payment
UC18_A |  |  |  |  | View Payments
UC10_S |  |  |  |  | Leave Review

## Database Structure
Database Structure
Team Name: | Essential Minds

## CRUD Analysis
CRUD Analysis
Dev Crew Name: |  | Essential Minds
Use Case Id | Use Case Name | User | Student | Instructor | Admin | InstructorApp | Availability | LessonOffering | Booking | Payment | Review | LessonProgress
UC01_SI | Register Account | C | C | C |  | C | [6 empty] | C | Create
UC02_SI | Edit Profile | RU | RU | RU | [8 empty] | R | Read
UC16_A | Review Instructor Application |  |  | U |  | RU | [6 empty] | U | Update
UC17_A | Manage Users | RUD | RUD | RUD | R | [7 empty] | D | Delete
UC11_I | Manage Availability |  |  | R |  |  | CRUD
UC12_I | Manage Lesson Offering |  |  | R |  |  |  | CRUD
UC04_S | Search Instructor |  |  | R |  |  | R | R
UC05_S | View Instructor Profile |  |  | R |  |  | R | R |  |  | R
UC06_S | Make Booking Request |  |  | R |  |  | R | R | C
UC13_I | View Booking Requests | [7 empty] | R
UC14_I | Respond to Booking Requests | [7 empty] | RU
UC07_S | View Booking Requests |  | R | [5 empty] | R | R
UC11_SI | Manage Bookings | [7 empty] | RU
UC08_S | Upload Proof of Payment | [7 empty] | RU | CRU
UC15_I | Verify Payment | [7 empty] | U | RU
UC18_A | View Payments |  | R | [5 empty] | R | R
UC20_A | Provide Lesson Feedback |  |  | R |  |  |  |  | R |  |  | C
UC03_S | View Lesson Progress |  | R | [5 empty] | R |  |  | R
UC09_I | View Completed Lessons |  | R |  |  |  |  | R | R
UC10_S | Leave Review |  | R | U |  |  |  |  | R |  | C
UC19_A | Monitor Bookings |  | R | R |  |  |  |  | R | R